## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Standards | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team 1 | 2026-02-12 | Missing values in dataset causing errors | Sprint 1 | Backend Team | Logical | Handled missing values using imputation (mean/mode) | 2026-02-13 | Closed | Data cleaned successfully
2 | Team 1 | 2026-02-14 | Feature Engineering Date column not usable for model | Sprint 1 | Backend Team | Logical | Converted date into processing time (days) | 2026-02-15 | Closed | Feature ready for training
3 | Team 1 | 2026-03-10 | Model giving low accuracy | Sprint 3 | Backend Team | Standards | Normalized data and tuned parameters | 2026-03-11 | Closed | Accuracy improved
4 | Team 1 | 2026-03-14 | Output showing unrealistic values | Sprint 3 | Backend Team | Logical | Balanced dataset and retrained model | 2026-03-15 | Closed | Predictions stabilized
5 | Team 1 | 2026-03-19 | Model not loading in app | Sprint 4 | Frontend Team | Maintainability | Fixed path and loaded model using joblib | 2026-03-20 | Closed | System integration successful
6 | Team 1 | 2026-03-20 | Incorrect prediction for inputs | Sprint 4 | Backend Team | Logical | Aligned input pipeline with training | 2026-03-21 | Closed | Consistent predictions achieved
7 | Team 1 | 2026-03-22 | Input form accepting invalid data | Sprint 4 | Frontend Team | User Interface | No validation rules | 2026-03-23 | Closed | Validation rules are added
8 | Team 1 | 2026-03-25 | UI not displaying prediction | Sprint 4 | Frontend Team | User Interface | Fixed display logic in Streamlit | 2026-03-26 | Closed | Output visible correctly
9 | Team 1 | 2026-03-26 | App crashing after deployment | Sprint 4 | Backend Team | Maintainability | Updated requirements.txt | 2026-03-27 | Closed | App runs smoothly
10 | Team 1 | 2026-03-28 | Model not working in deployed app | Sprint 4 | Frontend Team | Maintainability | Included model files in deployment | 2026-03-29 | Closed | Deployment successful

## Sheet2
Logical
User Interface
Maintainability
Standards
Others